## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a value 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Project Plan
Product Owner: | Teachers and the Team
Scrum Master: | Joel
Team: | Waltteri, Joona, Joel
Project Plan
Election Machine: Mayoral election of Hämeenlinna.
Language: English
Working method: Coding from 9-16, mainly in the time slots reserved. Scrum method included.
Required features (atleast one):
1. In the program, functionality needed is for admin to add, edit and remove candidates.
2. In the program, functionality needed is for admin to add, edit and remove questions (statements). [Done]
3. In the program, functionality needed is for candidates to answer the questions and edit and delete their answers.
4. In the program, functionality needed for an end user to answer the questions
- and see the candidate or candidates which best match to the answers of the end user, so that the end user can select whom to vote.

## Product Backlog
Product Backlog - Mayoral election of Hämeenlinna
ID | User Story | Story Point(s) | Priority
1 | As an admin, I am able to add, edit and remove candidates. | 10 | 3 | High | Medium | Low
2 | As an admin, I am able to edit, add and remove questions. | 10 | 5 | 5 | 3 | 1
3 | As a candidate, I am able to answer the questions and edit and remove them later. | 8 | 3
4 | As an voter, I am able to answer the questions. | 10 | 5
5 | As an voter, I am able to see the candidate or candidates which best match to my answers. | 16 | 3
6 | As an candidate, I am able to set my personal information and edit them later. | 8 | 3
7 | As an admin, I should be able to log in. | 6 | 1
8 | As a voter, I should be able to take a closer look over the candidates. | 4 | 3
9 | As an candidate, I should be able to log in. | 6 | 1
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a value 1 and other story 2. The one with the value 2 means that it requires double effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## Sprint Planning Meetings
Spring Planning | Participants
Week 1 | Waltteri | Joona | Joel
Online | X | X | X | If physically present mark X
2022-03-23
Week 2
Live - Campus
2022-03-31 | X | X | X
Week 3
Online
2022-04-07 | X | X | X
Week 15
Location
Date
Week 16
Location
Date
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint Backlog 1
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #2: As an admin, I am able to edit, add and remove questions.
Task : Planning database structure | 3 | Team | Done | 3
Task : Creating User Interface | 8 | Joel | Waiting
Task : Creating the individual databases | 2 | Team | Done | 1
Task : Creating GitHub repository | 2 | Team | Done |  |  |  | 3 | 1
Task : Creating Eclipse project | 1 | Team | Done |  | 0.1 |  | 1.5 | 1
Task : Planning classes and methods in the project | 4 | Team | Done |  |  |  | 2
Task : Planning the questions | 2 | Joel | Done |  |  | 1 | 0.5
Task : Creating code that runs questions into database | 4 | Joona | Ongoing |  |  |  |  | 0.5
Task : Creating code to edit and remove questions from database | 6 | Waltteri | Ongoing |  |  |  |  | 0.5
TOTAL |  |  |  | 4 | 0.1 | 1 | 7 | 3
[6 empty] | Yhteensä | 15.1
Sprint Goal:
- User Story #2 functioning
- Databases
- GitHub repo
Sprint Review & Retrospective:
- Databases
- GitHub repo
Not done / ongoing
- User Story #2 functioning
- Partly done, examined the fishapp and started to make some changes to the code
Pros:
-Project management and planning is DIAMOND
-Project started
-Teacher/ customer finally cleared the project vision and goal
Cons:
-Frustrating and passive-aggressive communication
-Technical difficulties
-Poor information about the goal

## Sprint Backlog 2
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #2: As an admin, I am able to edit, add and remove questions.
Task : Creating code that runs questions into database | 4 | Joona | Done |  |  |  | 2
- add function |  | Waltteri | Done |  |  | 1.5
Task : Creating code to edit and remove questions from database | 6 | Waltteri | Done | 1
- edit function |  | Waltteri | Done |  |  | 1.5
- remove function |  | Team | Done |  |  |  |  | 1.5
- read function |  | Joona | Done |  |  | 2
Task : Creating User Interface (admin) | 8 | Joel | Done |  |  | 1.5
- Creating page styles and buttons |  | Joel | Done |  |  |  | 2
- Modifying .jsp files |  | Team | Done |  |  |  |  | 1
TOTAL |  |  |  | 1 | 0 | 6.5 | 4 | 2.5
[6 empty] | Yhteensä | 14
Sprint Goal:
- User Story #2 functioning
Sprint Review & Retrospective:
- User Story #2 functioning
Not done / ongoing
-
Pros:
- Communication much more better than last sprint
- Teamwork, helping others to solve problems
- Working with divided duties worked well, altough still helped each others
Cons:
-Technical difficulties with GitHub, GitHub desktop and Eclipse
- Pre-review was extremely confusing

## Sprint Backlog 3
Sprint Backlog : Sprint 3
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1: As an admin, I am able to add, edit and remove candidates.
Task 1 : Creating code to edit and remove candidates from database
- edit function |  | Joona | Done |  | 0.5 | 0.5
- remove function |  | Joel | Done |  | 1 | 0.5
- read functions |  | Waltteri | Done |  | 0.5
- creating data class (Candidates.java) |  | Joona | Done |  | 0.5
Task 2 : Creating UI
- Creating page styles and buttons |  | Waltteri | Done |  | 0.5 | 1
- Creating .jsp files |  | Waltteri | Done |  | 1
Task 3 : Creating code that runs candidates into database
- add function |  | Joel | Done |  | 1.5
Task 4 : Candidate classes & methods
- class names |  | Team | Done | 1
- method & attribute names |  | Team | Done |  | 0.5
TOTAL |  |  |  | 1 | 6 | 2 | 0 | 0
[6 empty] | Yhteensä | 9
Sprint Goal:
- User Story #1 functioning
Sprint Review & Retrospective:
-
Not done / ongoing
-
Pros:
-
Cons:
-

## DB Tables
MySQL
|  |  |  | username: | sikli
|  |  |  | passwd: | kukkuu
Questions |  | Candidates |  | Answers
Question_id * | int, not null, autoincrement | Candidate_ID * | int, not null, autoincrement | Question_id *
Question | varchar(100) | Surname | varchar(40) | Candidate_ID *
|  | First name | varchar(25) | Vastaus | int
|  | Cand_no | int(2)
|  | Age | int 2
|  | Hometown | varchar(20)
|  | Party | varchar(25)
|  | Profession | varchar(30)
|  | Descr | varchar(500)
Luontilauseet:
tällä näkee käyttäjät
select user();
mysql -u root -p
CREATE USER 'sikli'@'localhost' IDENTIFIED BY 'kukkuu';
CREATE DATABASE vaalikone;
GRANT ALL PRIVILEGES ON `vaalikone` . * TO 'sikli'@'localhost';
ALTER DATABASE vaalikone CHARACTER SET utf8mb4 COLLATE utf8mb4_unicode_ci;
-- create a table ehdokkaat (mysql does not bother the case of letters - in this case) CREATE TABLE CANDIDATES
(CANDIDATE_ID INTEGER NOT NULL AUTO_INCREMENT,
SURNAME VARCHAR(40),
FIRST_NAME VARCHAR(25),
CAND_NO INT(2),
AGE INT(2),
HOMETOWN VARCHAR(20),
PARTY VARCHAR(25),
PROFESSION VARCHAR (25),
DESCR VARCHAR(500),
PRIMARY KEY (CANDIDATE_ID)
);
-- create a table kysymykset
CREATE TABLE QUESTIONS
(QUESTION_ID INTEGER NOT NULL AUTO_INCREMENT,
QUESTION VARCHAR(100),
PRIMARY KEY (QUESTION_ID)
);
-- create a table vastaukset
CREATE TABLE ANSWERS
(CAND_ID INTEGER NOT NULL,
QUEST_ID INTEGER NOT NULL,
ANSWER INTEGER,
PRIMARY KEY (CAND_ID, QUEST_ID),
FOREIGN KEY(CAND_ID) REFERENCES CANDIDATES(CANDIDATE_ID),
FOREIGN KEY(QUEST_ID) REFERENCES QUESTIONS(QUESTION_ID)
);

## Questions
NO | QUESTION
1 | Hämeenlinnasta täytyy saada houkutteleva asuinpaikka nuorille perheille.
Hämeenlinna needs to be done a tempting place for young families to move in.
2 | Hämeenlinnan täytyy tavoitella seuraavaa kulttuuripääkaupunki-titteliä.
City of Hämeenlinna must aim for the next Capital of Culture title.
3 | Aulangon virkistysalueelle täytyy keskittää enemmän palveluja retkeilijöille ja matkailijoille.
More services for the campers, hikers and tourists must be centralized in the Aulanko recreation area.
4 | Aulangon ja Kantolan alueilla järjestettävä enemmän ulkoilmatapahtumia
More outdoor events must be organized in the Aulanko and Kantola areas.
5 | Kunnan perusopetuspaikkoja keskitettävä Hämeenlinnan alueelle.
Municipal basic education facilities must be centered in the Hämeenlinna area.
6 | Päivähoitopaikkoja on lisättävä Hämeenlinnan alueella.
Number of day care facilities must be increased in the Hämeenlinna area.
7 | Sosiaali- ja terveyspalveluita tarjottava enemmän kaupungin alueella.
More health and social services must be offered in the city area.

## Candidates
CANDIDATE | SNAME | FNAME | CAND_NO | AGE | HOMETOWN | PARTY | PROFESSION | DESCRIPTION
1 | Berg | Maria | 8 | 43 | Hattula | Orange | Communications Director | I will work for less administration, better leadership and more impressive services.
2 | Hiltunen | Jukka | 12 | 24 | Lammi | White | Student | I will do everything to make student welfare better. Cut off the bullying from the schools and give best practices for learning!
3 | Jalava | Jouko | 17 | 57 | Hämeenlinna | Blue | CEO | Good leadership improves welfare of the employees. We must secure adequate staff and make their voices heard!
4 | Yli-Suutari | Seppo | 22 | 55 | Hauho | Green | Entrepreneur | Rise the Hämeenlinna up with proper work!
5 | Arvén | Mathilda | 29 | 29 | Tervakoski | Purple | Sales Representative | We must provide adequate commute and support service capacities for now and in future at our own municipal!
6 | Kannisto | Leila | 44 | 35 | Iittala | Red | Nurse | I will do everything to realizate basic healthcare ja elderly commute services in the area of 7000 municipality.

## Classes & Methods
ADMIN CLASSES AND METHODS
Classes (questions)
M (model): | Dao.java | Question.java
V (view): | index.html | showkysmarits.jsp
C (controller): | Update.java | AddQuestion.java | Delete.java | ReadToUpdate.java | ShowQuestions.java
kursiivilla merkityt luokat on luotu jo, joten niitä ei luoda uudestaan
CANDIDATE CLASSES AND METHODS
Classes (candidates)
M (model): | Dao.java | Candidates.java
V (view): | (index.html) | managecandidates.jsp
C (controller): | CandUpdate.java | CandAdd.java | CandDelete.java | CandReadToUpdate.java | CandShowCandidates.java
Methods (candidates)
Dao | readAllCandidates | updateCandidates | deleteCandidate | readCandidate | addCandidate
Candidates.java | constructor | constructor(param) | getId | setId(int id) | setId(String id) | getCandidate() | setCandidate(?,?,?,?,?) | jne jne setterit ja getterit
CandUpdate.java | init | doGet | doPost
CandAdd.java | init | doGet | doPost | constructor
CandDelete.java | init | doGet
CandReadToUpdate.java | init | CandReadToUpdate | doGet
CandShowUpdates.java | init | CandShowUpdates | doGet
Luodaan kandidaateille olio kirjaimella c (samaan tyyliin kun kysymyksillä q)
CLASSES AND METHODS